## Slide 1: Work Breakdown Structure (WBS) in Project Management

## Slide 2: Project Management
Planning
Estimating
Scheduling
Define activities & deliverables
Time & Cost in terms of resource usage
Define sequence of tasks occurrence

## Slide 3: What is WBS?
A work breakdown structure is:
“A hierarchical decomposition of the total scope of work to be carried out by the project team to accomplish the project objectives and create the required deliverables.”

## Slide 4: WBS
A tool for breaking down a project into its components and activities.
Components are broken down to activities.
Activities to sub-activities and each lower-level sub-activity can be broken down to further details.
Stops till the tasks no longer remain decomposable.
Work packages are the smallest unit of work that a project can be broken down into when creating a Work Breakdown Structure (WBS).
A WBS element may be a product, data, a service, or any combination.
4

## Slide 5: Pupose
To break a complex project into manageable chunks.

## Slide 6: How to create WBS?
Done by project managers mostly
Determine and describe the project statement
Highlight all necessary phases in the project
  Sometimes the scope is divided to different phases depending upon project
  Lowest level not too detailed, not too large
Create deliverables
Check for completeness - is all the effort included?
Assign deliverables to each team
6

## Slide 7: WBS

## Slide 8: Type of WBS
1- Process-oriented WBS (Phase-based)
  A process-oriented WBS defines a project in terms of steps, work phases, or functions. This type of WBS is focused on the steps that need to be taken within individual disciplines to complete a project and typically phrases individual elements in verb form.
2- Deliverable-oriented WBS
  A deliverables-oriented WBS defines a project in terms of tangible deliverable components. Deliverables are typically a physical component or item needed to complete the overall project.

## Slide 9: Process-Oriented WBS

## Slide 10: Deliverable-oriented WBS

## Slide 11: Reasons to use WBS
It helps with the correct project organization.
It depicts whole project work needed for org.
It assists in describing the project scope to stakeholders.
It helps to distribute responsibilities.
Visualize each member’s activity & role in project.
It shows the project milestones and all the points to control.
Helpful in cost estimation, resource allocation, and time management improvements.
Minimize unnecessary work which leads to missed deadlines & scope creep issues

## Slide 12: Steps to build a WBS
Begin with the Charter, focusing on Objectives and Deliverables
Break the main product(s) down into sub-products
Set the structure to match how you’ll manage the project
Lowest level not too detailed, not too large
Identify support activities
Check for completeness - is all the effort included?
Assign work package to managers
12

## Slide 13: Levels in WBS
Starts with level 0 i.e. project title
Then make level 1, highest level breakdown of about 4-7 nodes depending on your project. Termed as control accounts
Then make level 2: work packages.
Level 3 are the tasks/activities to be performed
Follow the standard numbering scheme
13

## Slide 14: WBS levels
Library management Systems
Database
Front end application
Servers configuration
data structures used
Database creation
UI design
……
ER diagram

## Slide 15: WBS Formats
2 Formats
Outline (Indented Format)
Graphical Tree (Organizational Chart)

## Slide 16: Displaying the WBS Example of outlined WBS.
16

## Slide 17: Displaying the WBS Example of Graphical Tree WBS
17

## Slide 18
https://online.visual-paradigm.com/diagrams/features/work-breakdown-structure-software/

## Slide 19: Challaenges
Must have concrete knowledge of project
All tasks/ deliverables properly identified and quoted
Each task should be broken down into legit activities
19

## Slide 20: The Dictionary of the WBS
WBS
A WBS dictionary is a companion document to the WBS that describes each WBS element. For each WBS element, the WBS dictionary includes a statement of work, a list of associated activities, and a list of milestones.
Other information can include the responsible organisation, start and end dates, resources required.

## Slide 21: WBS Guidelines
21
Must be easy to understand
Ensure each element corresponds to a deliverable
Breakdown until you get accurate time and cost estimates
Covers all objectives

## Slide 22: WBS Guidelines
22
Should not be much detailed as project plan
May use a template if you have
Can evolve over time
Can be drawn using Gantt Pro, Word, Excel, MS Project, Visio etc.
Each level have no more than 7 items

## Slide 23: WBS Template
Component groups with a ‘+’ in front of them are ‘rolled up’ – subcomponents are hiden to reduce clutter
23

## Slide 24: WBS Check List
Does it define 100% of the work that will be produced by the project?
Does it use a coding structure so that each element has a unique ID that shows its place in the hierarchy e.g. 1.1, 1.2, 1.1.1, 1.1.2?
Will project stakeholders be able to understand the project scope from the WBS?
Does each level represent 100% of the work required to deliver the parent level?
Is the decomposition sufficient that the tasks required to deliver each work package can easily be identified?
Is it in the format that gives a clear graphical, textual or tabular breakdown of the project scope?
24

## Slide 25: WBS Check List
Does it have a least two levels with at least one level of decomposition?
Was it created by those who will be performing the work?
Is it being regularly updated as project changes are approved?
Can you identify one person who is accountable for each work package?
Can you clearly define the acceptance criteria for each work package?
Does it allow you to estimate costs accurately?
Does the WBS have logical summary elements that can be used in tracking progress and performance?
25

## Slide 26: Professional Tools used
https://www.projectmanager.com/
https://www.atlassian.com/software/jira
https://ganttpro.com/